## EXAMPLE - Creative Workflow
Creative Workflow Template
PROJECT TITLE |  |  |  |  | PROJECT MANAGER
Beta Branding Project |  |  |  |  | Hilda Wilson
* Due Dates that have passed and are not "Complete" are highlighted in red
PHASE | TASKS | OWNER | DUE DATE | STATUS | COMMENTS
1 | DEFINE GOALS AND ROLES |  | 2000-05-05 | In Progress
1 | Create creative brief |  | 2000-05-05 | Complete
1 | Define SMART goals |  | 2000-05-05 | Complete
1 | Set project KPIs |  | 2000-05-05 | Complete
1 | Hold kickoff call |  | 2000-05-06 | Complete
1 | Set project milestones |  | 2000-05-06 | Complete
1 | Set roles and responsibilities |  | 2000-05-06 | In Progress
1 | Create project timeline |  | 2000-05-06 | Not Started
2 | GENERATE AND DEVELOP IDEAS |  | 2034-05-17 | In Progress
2 | Brainstorm as a group |  | 2034-05-07 | Complete
2 | Record and share ideas |  | 2034-05-10 | On Hold
2 | Give feedback on ideas |  | 2034-05-11 | Approved
2 | Choose the winning ideas |  | 2034-05-15 | Review
2 | Begin developing assets |  | 2034-05-15
2 | Communicate regularly with stakeholders |  | 2034-05-17
3 | REVIEW AND APPROVAL |  | 2034-06-05
3 | Gather internal feedback |  | 2034-06-01
3 | Implement internal feedback |  | 2034-06-02
3 | Gather client feedback |  | 2034-06-03
3 | implement client feedback |  | 2034-06-04
3 | Get internal approval |  | 2034-06-05
3 | Get client approval |  | 2034-06-05
4 | PRODUCT LAUNCH AND MONITOR SUCCESS |  | 2034-06-28
4 | Publish or launch assets |  | 2034-06-21
4 | Start tracking KPIs |  | 2034-06-22
4 | Send invoices |  | 2034-06-23
4 | Share metrics with stakeholders |  | 2034-06-26
4 | Continue monitoring success |  | 2034-06-27
4 | Manage client questions |  | 2034-06-28
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Creative Workflow
Creative Workflow Template
PROJECT TITLE |  |  |  |  | PROJECT MANAGER
* Due Dates that have passed and are not "Complete" are highlighted in red
PHASE | TASKS | OWNER | DUE DATE | STATUS | COMMENTS
1 | DEFINE GOALS AND ROLES
1 | Create creative brief
1 | Define SMART goals
1 | Set project KPIs
1 | Hold kickoff call
1 | Set project milestones
1 | Set roles and responsibilities
1 | Create project timeline
2 | GENERATE AND DEVELOP IDEAS
2 | Brainstorm as a group
2 | Record and share ideas
2 | Give feedback on ideas
2 | Choose the winning ideas
2 | Begin developing assets
2 | Communicate regularly with stakeholders
3 | REVIEW AND APPROVAL
3 | Gather internal feedback
3 | Implement internal feedback
3 | Gather client feedback
3 | implement client feedback
3 | Get internal approval
3 | Get client approval
4 | PRODUCT LAUNCH AND MONITOR SUCCESS
4 | Publish or launch assets
4 | Start tracking KPIs
4 | Send invoices
4 | Share metrics with stakeholders
4 | Continue monitoring success
4 | Manage client questions

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Review
Approved
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.