## EXAMPLE Product Strategy Map
Product Strategy Roadmap
Released? | Feature Name | Feature ID | Feature Type | Feature Description | Assigned To | Progress Stage | Target Release | Start Date | End Date | Duration in Days | Status | PP | Rank | Dev Resources | Image
| Improve Iconography Resolution | 1234 | Series 1 |  | Alexandra M. | Production | Quarter 1 | 2028-01-16 | 2028-02-15 | 31 | In Progress | Medium | 2
Yes | Feature 1 | 2345 | Series 1 |  | Brian G. | Requirement | Quarter 1 | 2028-01-16 | 2028-02-02 | 18 | Complete | High | 1
No | Feature 2 | 4567 | Series 2 |  | Jason D. | Design | Quarter 1 | 2028-01-31 | 2028-02-05 | 6 | In Progress | Medium | 3
| Feature 3 | 2345 | Series 1 |  | Jason D. | Design |  | 2028-02-05 | 2028-02-15 | 11 | Not Started | Low | 4
| Workshopping |  | Series 3 |  | Jason D. | Requirement |  | 2028-01-22 | 2028-02-25 | 35 |  |  | 1
| Feature 1 |  | Series 8 |  | Alexandra M. | Design |  | 2028-01-22 | 2028-01-29 | 8 | Overdue |  | 2
| Feature 2 |  | Series 4 |  | Brian G. | Design |  | 2028-01-28 | 2028-01-31 | 4 | Needs Review |  | 2
| Feature 3 |  | Series 2 |  | Olivia C. | Requirement |  | 2028-01-29 | 2028-02-25 | 28 | Approved |  | 5
| Branding |  | Series 1 |  | Olivia C. | Production |  | 2028-02-28 | 2028-03-16 | 18 |  |  | 2
| Feature 1 |  | Series 3 |  | Alexandra M. |  |  | 2028-02-28 | 2028-03-01 | 3 | On Hold |  | 1
| Feature 2 |  | Series 6 |  | Krista A. |  |  | 2028-02-28 | 2028-03-04 | 6 |  |  | 1
| Feature 3 |  | Series 1 |  | Jason D. |  |  | 2028-03-01 | 2028-03-16 | 16 |  |  | 3
| Testing Stage Alpha |  | Series 3 |  | Jason D. |  | Quarter 2 | 2028-03-16 | 2028-04-16 | 32 |  |  | 4
| Feature 1 |  | Series 2 |  | Jason D. |  |  | 2028-03-16 | 2028-03-17 | 2 |  |  | 4
| Feature 2 |  | Series 3 |  | Jason D. |  |  | 2028-03-18 | 2028-03-20 | 3 |  |  | 4
| Feature 3 |  | Series 2 |  | Alexandra M. |  |  | 2028-03-24 | 2028-04-16 | 24 |  |  | 2
| Testing Stage Beta |  | Series 2 |  | Brian G. |  |  | 2028-03-24 | 2028-04-21 | 29 |  |  | 2
| Feature 1 |  | Series 3 |  | Olivia C. |  |  | 2028-03-24 | 2028-03-26 | 3 |  |  | 5
| Feature 2 |  | Series 1 |  | Olivia C. |  |  | 2028-03-26 | 2028-04-05 | 11 |  |  | 1
| Feature 3 |  | Series 1 |  | Krista A. |  |  | 2028-04-06 | 2028-04-21 | 16 |  |  | 2
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Product Strategy Map
Product Strategy Roadmap
Released? | Feature Name | Feature ID | Feature Type | Feature Description | Assigned To | Progress Stage | Target Release | Start Date | End Date | Duration in Days | Status | Release Target Confidence | Rank | Dev Resources | Image
[8 empty] | 2028-01-16 | 2028-02-15 | 31 | In Progress | Medium | 2
Yes | [7 empty] | 2028-01-16 | 2028-02-02 | 18 | Complete | High | 1
No | [7 empty] | 2028-01-31 | 2028-02-05 | 6 | In Progress | Medium | 3
[8 empty] | 2028-02-05 | 2028-02-15 | 11 | Not Started | Low | 4
[8 empty] | 2028-01-22 | 2028-02-25 | 35 |  |  | 1
[8 empty] | 2028-01-22 | 2028-01-29 | 8 | Overdue |  | 2
[8 empty] | 2028-01-28 | 2028-01-31 | 4 | Needs Review |  | 2
[8 empty] | 2028-01-29 | 2028-02-25 | 28 | Approved |  | 5
[8 empty] | 2028-02-28 | 2028-03-16 | 18 |  |  | 2
[8 empty] | 2028-02-28 | 2028-03-01 | 3 | On Hold |  | 1
[8 empty] | 2028-02-28 | 2028-03-04 | 6 |  |  | 1
[8 empty] | 2028-03-01 | 2028-03-16 | 16 |  |  | 3
[8 empty] | 2028-03-16 | 2028-04-16 | 32 |  |  | 4
[8 empty] | 2028-03-16 | 2028-03-17 | 2 |  |  | 4
[8 empty] | 2028-03-18 | 2028-03-20 | 3 |  |  | 4
[8 empty] | 2028-03-24 | 2028-04-16 | 24 |  |  | 2
[8 empty] | 2028-03-24 | 2028-04-21 | 29 |  |  | 2
[8 empty] | 2028-03-24 | 2028-03-26 | 3 |  |  | 5
[8 empty] | 2028-03-26 | 2028-04-05 | 11 |  |  | 1
[8 empty] | 2028-04-06 | 2028-04-21 | 16 |  |  | 2
CLICK HERE TO CREATE IN SMARTSHEET
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
Yes/No | Priority | Status | Rank
Yes | Low | Not Started | 1
No | Medium | In Progress | 2
| High | Complete | 3
|  | Needs Review | 4
|  | Approved | 5
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.