## EXAMPLE - Project Status Report
Multiple Project Status Report Template Example
|  |  |  | Projects |  |  | Deliverable(s) |  | Cost / Hours
At Risk | Status | Priority | Deadline | Task | Description | Assigned To | Deliverable | % Done | Fixed Cost | Estimated Hours | Actual Hours
Project One
| Complete | High | MM/DD/YY | Develop Initial Wireframes | Create initial screen layouts for core user flows. | Krista Ahmed | Wireframes Package | 100% | 2000 | 4 | 3
| In Progress | Medium | MM/DD/YY | Draft Content Strategy | Outline messaging themes and main website content sections. | Leigh Gibbs | Content Strategy Draft | 80% | 5500 | 2 | 3
| Not Started | Low | MM/DD/YY | Set Up Development Environment | Install software and configure tools for project development. | Lori Garcia | Development Environment Setup | 30% | 2400 | 4 | 5
| On Hold | Low | MM/DD/YY | Conduct Internal Review | Collect internal feedback and document requested revisions. | Makara McLean | Internal Review Report | 0% | 5560 | 2 | 1
| Overdue | Medium | MM/DD/YY | Finalize Feature Requirements | Finalize functional requirements and system feature list. | Marta Hicks | Finalized Feature Requirements | 10% | 9843 | 1 | 1
| Complete | High |  | Project Two
| Complete | High | MM/DD/YY | Design Landing Page | Design and export landing page visuals and assets. | Mateus Tobin | Landing Page Design Files
| Complete | High | MM/DD/YY | Implement Core Modules | Build software modules required for MVP functionality. | Olivia Carter | Core Module Build
| Complete | High | MM/DD/YY | Conduct Integration Testing | Run tests across integrated systems and modules. | Petrus Nishimura | Integration Test Plan Execution
| Complete | High | MM/DD/YY | Launch Pilot Release | Deploy pilot version for early user feedback. | Raghu Prakash | Pilot Release Deployment
| Complete | High |  | Project Three
| Complete | High |  | Gather Client Feedback | Summarize pilot user feedback for review and action. | Romy Bailey | Client Feedback Summary
| Complete | High |  | Create Training Materials | Prepare training manuals and user guides. | Sarah Goodwin | Training Materials Kit
| Complete | High |  | Update User Documentation | Update documentation to reflect final project changes. | Sasha Petrov | Updated User Documentation
| Complete | High |  | Run Final QA Pass | Summarize QA test results and track any final defects. | Tamika Marshall | Final QA Report
| Complete | High |  | Launch Public Release | Release the production version with full features live. | Victoria Pearson | Public Launch Delivery
| Complete | High
| Complete | High
| Complete | High
| Complete | High
| Complete | High
| Complete | High
| Complete | High
| Complete | High
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Project Status Report
Multiple Project Status Report Template
|  |  |  | Projects |  |  | Deliverable(s) |  | Cost / Hours
At Risk | Status | Priority | Deadline | Task | Description | Assigned To | Deliverable | % Done | Fixed Cost | Estimated Hours | Actual Hours
Project One
| Complete | High | MM/DD/YY | Task 1 | Task description here… |  |  | 0% | 0 | 0 | 0
| In Progress | Medium
| Not Started | Low
| On Hold | Low
| Overdue | Medium
| Complete | High |  | Project Two
| Complete | High
| Complete | High
| Complete | High
| Complete | High
| Complete | High |  | Project Three
| Complete | High
| Complete | High
| Complete | High
| Complete | High
| Complete | High
| Complete | High
| Complete | High
| Complete | High
| Complete | High
| Complete | High
| Complete | High
| Complete | High
| Complete | High

## Dropdown Key - DO NOT DELETE
DROPDOWN KEYS - DO NOT DELETE
STATUS KEY | PRIORITY KEY
Not Started | High
In Progress | Medium
Complete | Low
On Hold
Overdue

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.