## Multiple Project Tracking EX
Multiple Project Tracking Template Example
Company Name |  |  |  |  | Start Date
2055-03-31
|  | Projects | [5 empty] | Deliverables |  | Cost / Hours |  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16 |  |  |  |  | Week 17 |  |  |  |  | Week 18 |  |  |  |  | Week 19 |  |  |  |  | Week 20
Status | Priority | Project Names + Task Titles | Task Description | Task Owner | Start Date | End Date | # of Days | Deliverable | % Complete | Fixed Cost | Est. Hours | Actual Hours | time axis 2055-03-29 to 2055-08-13
In Progress | High | Project 1 |  |  | 2055-03-31 | 2055-04-21 | 16 |  | 74.33% | 22530 | 306 | 298 | bar: 2055-03-29 to 2055-08-13
In Progress | Medium | P1 Task 1 |  |  | 2055-03-31 | 2055-04-03 | 3 |  | 33% | 8500 | 32 | 36 | bar: 2055-03-31 to 2055-04-02
On Hold | Medium | P1 Task 2 |  |  | 2055-04-02 | 2055-04-18 | 11 |  | 100% | 2500 | 104 | 100 | bar: 2055-04-02 to 2055-04-16
Overdue | High | P1 Task 3 |  |  | 2055-04-13 | 2055-04-18 | 4 |  | 90% | 3200 | 40 | 40 | bar: 2055-04-13 to 2055-04-16
Needs Review | Low | P1 Task 4 |  |  | 2055-04-03 | 2055-04-12 | 6 |  | 33% | 750 | 50 | 56 | bar: 2055-04-05 to 2055-04-12
Complete | Medium | P1 Task 5 |  |  | 2055-04-09 | 2055-04-20 | 8 |  | 100% | 6380 | 64 | 56 | bar: 2055-04-09 to 2055-04-20
Needs Update | High | P1 Task 6 |  |  | 2055-04-18 | 2055-04-21 | 3 |  | 90% | 1200 | 16 | 10 | bar: 2055-04-19 to 2055-04-21
In Progress | Medium | Project 2 |  |  | 2055-04-22 | 2055-06-21 | 43 |  | 21.67% | 16700 | 792 | 367 | bar: 2055-03-29 to 2055-08-13
Needs Update | Low | P2 Task 1 |  |  | 2055-04-22 | 2055-06-21 | 43 |  | 70% | 2200 | 350 | 356 | bar: 2055-04-22 to 2055-06-21
In Progress | High | P2 Task 2 |  |  | 2055-04-30 | 2055-05-02 | 1 |  | 60% | 14500 | 20 | 11 | bar: 2055-04-30
Not Started | Low | P2 Task 3 |  |  | 2055-05-05 | 2055-06-19 | 33 |  | 0% |  | 272 | bar: 2055-05-05 to 2055-06-18
Not Started | Low | P2 Task 4 |  |  | 2055-05-06 | 2055-06-03 | 21 |  | 0% |  | 150 | bar: 2055-05-06 to 2055-06-03
|  | P2 Task 5 |  |  |  |  | 0 |  | 0%
|  | P2 Task 6 |  |  |  |  | 0 |  | 0%
Overdue | Low | Project 3 |  |  | 2055-04-14 | 2055-04-25 | 8 |  | 74.33% | 8350 | 112 | 99 | bar: 2055-03-29 to 2055-08-13
On Hold | Medium | P3 Task 1 |  |  | 2055-04-14 | 2055-04-18 | 3 |  | 33% | 6500 | 40 | 36 | bar: 2055-04-14 to 2055-04-16
Complete | High | P3 Task 2 |  |  | 2055-04-15 | 2055-04-16 | 2 |  | 100% |  | 16 | 12 | bar: 2055-04-15 to 2055-04-16
In Progress | Low | P3 Task 3 |  |  | 2055-04-17 | 2055-04-17 | 0 |  | 90% |  | 5 | 5
Overdue | Low | P3 Task 4 |  |  | 2055-04-21 | 2055-04-24 | 3 |  | 33% |  | 32 | 22 | bar: 2055-04-21 to 2055-04-23
Complete | Low | P3 Task 5 |  |  | 2055-04-22 | 2055-04-23 | 2 |  | 100% | 1850 | 14 | 16 | bar: 2055-04-22 to 2055-04-23
Needs Review | Medium | P3 Task 6 |  |  | 2055-04-25 | 2055-04-25 | 0 |  | 90% |  | 5 | 8
|  | Project 4 |  |  | 0 | 0 | 0 |  | 0% | 0 | 0 | 0
|  | P4 Task 1 |  |  |  |  | 0 |  | 0%
|  | P4 Task 2 |  |  |  |  | 0 |  | 0%
|  | P4 Task 3 |  |  |  |  | 0 |  | 0%
|  | P4 Task 4 |  |  |  |  | 0 |  | 0%
|  | P4 Task 5 |  |  |  |  | 0 |  | 0%
|  | P4 Task 6 |  |  |  |  | 0 |  | 0%
|  | Project 5 |  |  | 0 | 0 | 0 |  | 0% | 0 | 0 | 0
|  | P5 Task 1 |  |  |  |  | 0 |  | 0%
|  | P5 Task 2 |  |  |  |  | 0 |  | 0%
|  | P5 Task 3 |  |  |  |  | 0 |  | 0%
|  | P5 Task 4 |  |  |  |  | 0 |  | 0%
|  | P5 Task 5 |  |  |  |  | 0 |  | 0%
|  | P5 Task 6 |  |  |  |  | 0 |  | 0%
CLICK HERE TO CREATE IN SMARTSHEET

## Multiple Project Tracking BL
Multiple Project Tracking Template
Company Name |  |  |  |  | Start Date
[5 empty] | 2055-03-31 |  |  | <-- Enter initial Start Date to populate Timeline dates.
|  | Projects | [5 empty] | Deliverables |  | Cost / Hours |  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16 |  |  |  |  | Week 17 |  |  |  |  | Week 18 |  |  |  |  | Week 19 |  |  |  |  | Week 20
Status | Priority | Project Names + Task Titles | Task Description | Task Owner | Start Date | End Date | # of Days | Deliverable | % Complete | Fixed Cost | Est. Hours | Actual Hours | time axis 2055-03-29 to 2055-08-13
|  | Project 1 |  |  | 0 | 0 | 0 |  | 0% | 0 | 0 | 0
|  | P1 Task 1 |  |  |  |  | 0 |  | 0%
|  | P1 Task 2 |  |  |  |  | 0 |  | 0%
|  | P1 Task 3 |  |  |  |  | 0 |  | 0%
|  | P1 Task 4 |  |  |  |  | 0 |  | 0%
|  | P1 Task 5 |  |  |  |  | 0 |  | 0%
|  | P1 Task 6 |  |  |  |  | 0 |  | 0%
|  | Project 2 |  |  | 0 | 0 | 0 |  | 0% | 0 | 0 | 0
|  | P2 Task 1 |  |  |  |  | 0 |  | 0%
|  | P2 Task 2 |  |  |  |  | 0 |  | 0%
|  | P2 Task 3 |  |  |  |  | 0 |  | 0%
|  | P2 Task 4 |  |  |  |  | 0 |  | 0%
|  | P2 Task 5 |  |  |  |  | 0 |  | 0%
|  | P2 Task 6 |  |  |  |  | 0 |  | 0%
|  | Project 3 |  |  | 0 | 0 | 0 |  | 0% | 0 | 0 | 0
|  | P3 Task 1 |  |  |  |  | 0 |  | 0%
|  | P3 Task 2 |  |  |  |  | 0 |  | 0%
|  | P3 Task 3 |  |  |  |  | 0 |  | 0%
|  | P3 Task 4 |  |  |  |  | 0 |  | 0%
|  | P3 Task 5 |  |  |  |  | 0 |  | 0%
|  | P3 Task 6 |  |  |  |  | 0 |  | 0%
|  | Project 4 |  |  | 0 | 0 | 0 |  | 0% | 0 | 0 | 0
|  | P4 Task 1 |  |  |  |  | 0 |  | 0%
|  | P4 Task 2 |  |  |  |  | 0 |  | 0%
|  | P4 Task 3 |  |  |  |  | 0 |  | 0%
|  | P4 Task 4 |  |  |  |  | 0 |  | 0%
|  | P4 Task 5 |  |  |  |  | 0 |  | 0%
|  | P4 Task 6 |  |  |  |  | 0 |  | 0%
|  | Project 5 |  |  | 0 | 0 | 0 |  | 0% | 0 | 0 | 0
|  | P5 Task 1 |  |  |  |  | 0 |  | 0%
|  | P5 Task 2 |  |  |  |  | 0 |  | 0%
|  | P5 Task 3 |  |  |  |  | 0 |  | 0%
|  | P5 Task 4 |  |  |  |  | 0 |  | 0%
|  | P5 Task 5 |  |  |  |  | 0 |  | 0%
|  | P5 Task 6 |  |  |  |  | 0 |  | 0%

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
Priority | Status
High | Complete
Medium | In Progress
Low | Overdue
Not Started
On Hold
Needs Review
Approved

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.