## EXAMPLE Project Budget Tracker
Project Budget Tracking Template Example
User to complete non-shaded cells only. | [5 empty] | LABOR |  |  | MATERIALS |  |  | FIXED |  |  | BALANCE
TASK | DESCRIPTION | STATUS | PLANNED START DATE | ACTUAL START DATE | END DATE | HR | $/HR | TOTAL LABOR | UNITS | $/UNITS | TOTAL MATERIALS | TRAVEL | EQUIPMENT / SPACE | MISC. | BUDGET | ACTUAL | UNDER/OVER
PROJECT 1
Task |  | Not Started |  |  |  | 4 | 40 | 160 | 12 | 15 | 180 | 500 | 600 | 50 | 200 | 1490 | 1290
Task |  | In Progress |  |  |  | 8 | 15 | 120 | 22 | 14 | 308 | 200 | 600 | 100 | 1500 | 1328 | -172
Task |  | Complete | [5 empty] | 0 | 50 | 11 | 550 |  |  | 300 | 100 | 850 | 750
Subtask |  | Needs Review |  |  |  | 6 | 10 | 60 | 44 | 45 | 1980 |  |  |  | 2040 | 2040 | 0
Subtask |  | Approved | [5 empty] | 0 | 3 | 500 | 1500 |  |  | 7500 | 12500 | 9000 | -3500
Subtask |  | Overdue | [5 empty] | 0 |  |  | 0 |  |  |  |  | 0 | 0
Subtask |  | On Hold | [5 empty] | 0 |  |  | 0 |  |  |  |  | 0 | 0
Task | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 | 0
Task | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 | 0
SUBTOTAL | [7 empty] | 340 |  |  | 4518 | 700 | 1200 | 7950 | 16340 | 14708 | -1632
User to complete non-shaded cells only. | [5 empty] | LABOR |  |  | MATERIALS |  |  | FIXED |  |  | BALANCE
TASK | DESCRIPTION | STATUS | PLANNED START DATE | ACTUAL START DATE | END DATE | HR | $/HR | TOTAL LABOR | UNITS | $/UNITS | TOTAL MATERIALS | TRAVEL | EQUIPMENT / SPACE | MISC. | BUDGET | ACTUAL | UNDER/OVER
PROJECT 2
Task |  | Not Started |  |  |  | 5 | 50 | 250 |  |  | 0 |  |  |  | 200 | 250 | 50
Task |  | In Progress | [5 empty] | 0 |  |  | 0 |  | 1100 |  | 1500 | 1100 | -400
Task |  | Complete | [5 empty] | 0 | 1 | 150 | 150 |  |  |  | 100 | 150 | 50
Subtask |  | Needs Review | [5 empty] | 0 |  |  | 0 | 1800 |  |  | 2040 | 1800 | -240
Subtask |  | Approved | [5 empty] | 0 |  |  | 0 |  | 25000 |  | 23500 | 25000 | 1500
Subtask |  | Overdue |  |  |  | 85 | 75.5 | 6417.5 |  |  | 0 |  |  |  | 2500 | 6417.5 | 3917.5
Subtask |  | On Hold | [5 empty] | 0 |  |  | 0 |  |  |  |  | 0 | 0
Task | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 | 0
Task | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 | 0
SUBTOTAL | [7 empty] | 6667.5 |  |  | 150 | 1800 | 26100 | 0 | 29840 | 34717.5 | 4877.5
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Project Budget Tracker
Project Budget Tracking Template
User to complete non-shaded cells only. | [5 empty] | LABOR |  |  | MATERIALS |  |  | FIXED |  |  | BALANCE
TASK | DESCRIPTION | STATUS | PLANNED START DATE | ACTUAL START DATE | END DATE | HR | $/HR | TOTAL LABOR | UNITS | $/UNITS | TOTAL MATERIALS | TRAVEL | EQUIPMENT / SPACE | MISC. | BUDGET | ACTUAL | UNDER/OVER
PROJECT 1
Task | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 | 0
Task | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 | 0
Task | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 | 0
Task | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 | 0
Task | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 | 0
Task | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 | 0
Task | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 | 0
Task | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 | 0
Task | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 | 0
SUBTOTAL | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
User to complete non-shaded cells only. | [5 empty] | LABOR |  |  | MATERIALS |  |  | FIXED |  |  | BALANCE
TASK | DESCRIPTION | STATUS | PLANNED START DATE | ACTUAL START DATE | END DATE | HR | $/HR | TOTAL LABOR | UNITS | $/UNITS | TOTAL MATERIALS | TRAVEL | EQUIPMENT / SPACE | MISC. | BUDGET | ACTUAL | UNDER/OVER
PROJECT 2
Task | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 | 0
Task | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 | 0
Task | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 | 0
Task | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 | 0
Task | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 | 0
Task | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 | 0
Task | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 | 0
Task | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 | 0
Task | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 | 0
SUBTOTAL | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.