## EXAMPLE Project Time Tracking
Project Time Tracking Template Example
Project Name |  |  | Start Date
Project Beta |  |  | 2024-01-02
Project Manager |  |  | End Date
Aila Kishimoto |  |  | 2024-03-26
Project Status |  |  | Project Duration in Days
In Progress |  |  | 85 | < auto calculates
auto-calculates
AT RISK | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
Yes | PROJECT CONCEPTION AND INITIATION | Complete | Karl Peter | 2024-01-02 | 2024-02-09 | 39
No | – Project Charter | In Progress | Makara McLean | 2024-01-02 | 2024-01-11 | 10
Yes | –– Project Charter Revisions | On Hold | Makara McLean | 2024-01-07 | 2024-01-11 | 5
Yes | – Research | In Progress | Krisa Ahmed | 2024-01-10 | 2024-02-23 | 45
No | – Projections | In Progress | Krisa Ahmed | 2024-01-10 | 2024-01-20 | 11
No | – Stakeholders | Complete | Karl Peter | 2024-01-16 | 2024-01-29 | 14
No | – Guidelines | In Progress | Karl Peter | 2024-01-19 | 2024-02-01 | 14
No | – Project Initiation | Complete | Brennan Gardiner | 2024-01-22 | 2024-02-09 | 19
No | PROJECT DEFINITION AND PLANNING | Not Started | Aila Kishimoto | 2024-01-28 | 2024-02-14 | 18
Yes | – Scope & Goal Setting | Not Started | Brennan Gardiner | 2024-01-28 | 2024-02-06 | 10
No | – Budget | Not Started | Makara McLean | 2024-01-31 | 2024-02-02 | 3
No | – Communication Plan | Not Started | Krisa Ahmed | 2024-02-04 | 2024-02-12 | 9
No | – Risk Management | Not Started | Krisa Ahmed | 2024-02-06 | 2024-02-14 | 9
No | PROJECT LAUNCH & EXECUTION | In Progress |  | 2024-02-18 | 2024-03-26 | 38
No | – Status & Tracking | Complete |  | 2024-02-18 | 2024-02-20 | 3
No | – KPIs | Complete |  | 2024-02-18 | 2024-02-23 | 6
No | –– Monitoring | On Hold |  | 2024-02-18 | 2024-02-26 | 9
No | –– Forecasts | In Progress |  | 2024-02-21 | 2024-02-23 | 3
No | – Project Updates | In Progress |  | 2024-02-22 | 2024-02-23 | 2
No | –– Chart Updates | In Progress |  | 2024-02-25 | 2024-03-26 | 31
No | PROJECT PERFORMANCE / MONITORING | On Hold |  | 2024-02-25 | 2024-03-26 | 31
No | – Project Objectives | Not Started |  | 2024-02-25 | 2024-02-28 | 4
No | – Quality Deliverables | In Progress |  | 2024-02-26 | 2024-03-03 | 7
No | – Effort & Cost Tracking | In Progress |  | 2024-02-25 | 2024-03-06 | 11
No | – Project Performance | In Progress |  | 2024-03-03 | 2024-03-26 | 24
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Project Time Tracking
Project Time Tracking Template
Project Name |  |  | Start Date
Project Manager
Project Status |  |  | Project Duration in Days
|  |  | 1 | < auto calculates
auto-calculates
AT RISK | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
Yes | Task | Complete |  |  |  | 1
No | Subtask | In Progress |  |  |  | 1
Yes |  | On Hold |  |  |  | 1
Yes |  | In Progress |  |  |  | 1
No |  | In Progress |  |  |  | 1
No |  | Complete |  |  |  | 1
No |  | In Progress |  |  |  | 1
No |  | Complete |  |  |  | 1
No | Task | Not Started |  |  |  | 1
Yes | Subtask | Not Started |  |  |  | 1
No |  | Not Started |  |  |  | 1
No |  | Not Started |  |  |  | 1
No |  | Not Started |  |  |  | 1
No | Task | In Progress |  |  |  | 1
No | Subtask | Complete |  |  |  | 1
No |  | Complete |  |  |  | 1
No |  | On Hold |  |  |  | 1
No |  | In Progress |  |  |  | 1
No |  | In Progress |  |  |  | 1
No |  | In Progress |  |  |  | 1
No | Task | On Hold |  |  |  | 1
No | Subtask | Not Started |  |  |  | 1
No |  | In Progress |  |  |  | 1
No |  | In Progress |  |  |  | 1
No |  | In Progress |  |  |  | 1
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Dropdown Keys - DO NOT DELETE
DROPDOWN KEYS - Do Not Delete
Status | Risk
Not Started | Yes
In Progress | No
Complete
On Hold

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.